## FIVE-YEAR ROAD RESURFACING
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: FIVE-YEAR ROAD RESURFACING PLAN
Project Total: $74,434,073
October 1, 2019 through September 30, 2025
Funded Program: N/A
District(s): Countywide
Project Description, Milestones and Service Impact
In FY 2017-18, the Board of County Commissioners approved a five-year funding plan to resurface a minimum of fifty-five (55) miles of roads countywide. This will decrease our current backlog in resurfacing and will result in savings of the reconstruction costs of a road, which can be 4 to 6 times greater than the cost to resurface roads. In FY 19-20, an additional $1,230,000 in General Fund was allocated to Road Resurfacing plan to increase annual target from fifty-five (55) miles of road resurfacing to sixty-three (63) miles of road resurfacing for FY 19-20. In FY 20-21 through FY 23-25, reflects an projected annual increase in CPI of 2.5 percent from; as well as, to be determined supplemental funding sources to meet the sixty-three (63) of road resurfacing within those fiscal years. In FY 20-21, a one-time transfer of Local Option Gas Tax will offset the resurfacing shortage; as well as, the CPI increase associated with resurfacing costs. Additionally, an anticipated balance forward total of $1,600,731 will be carried forward for utilization in FY21.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 746000 | 4445250 | 2920000 | 2920000 | 2920000 | 2920000 | 2920000 | 19791250
Fuel Taxes | 5820452 | 1600000 | 3319991 | 1600000 | 1600000 | 1600000 | 1600000 | 17140443
General Funds | 1651000 | 2881000 | 2881000 | 3026851 | 3102522 | 3180085 | 3180085 | 19902543
Ad Valorem Taxes | 635000 | 635000 | 635000 | 635000 | 635000 | 635000 | 635000 | 4445000
Other Financing Sources | 125000 | 125000 | 1773146 | 1994765 | 2923510 | 3106708 | 3106708 | 13154837
Total Revenue | 8977452 | 9686250 | 11529137 | 10176616 | 11181032 | 11441793 | 11441793 | 74434073
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Repayment of Short-Term Loan | 0 | 0 | 0 | 0 | 750000 | 750000 | 750000 | 2250000
Construction Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Road Resurfacing | 8977452 | 9686250 | 11529137 | 10176616 | 10431032 | 10691793 | 10691793 | 72184073
Total Expense | 8977452 | 9686250 | 11529137 | 10176616 | 11181032 | 11441793 | 11441793 | 74434073

## FIVE-YEAR ROAD RECONSTRUCTION
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: FIVE-YEAR RECONSTRUCTION PLAN
Project Total: $25,508,224
October 1, 2019 through September 30, 2025
Funded Program: N/A
District(s): Countywide
Project Description, Milestones and Service Impact
In FY 2017-2018, the Board of County Commissioners approved a five-year funding plan to reconstruct roadways as funding is available countywide. In FY 18-19 the Road and Bridge MSTUs were leverage in order to reconstruct 5.56 miles. In FY 19-20, the General Fund increased funding of $900,000 to the County's Road Reconstruction program. With the additional funding, 8 miles of road reconstruction will be accomplished in FY 19-20; this will decrease our current backlog in reconstruction. In FY20-21, Local Option Gas Tax will offset the funding shortfall, allowing 8 miles of reconstruction to be completed as anticipated.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Ad Valorem Taxes | 1019643 | 0 | 0 | 0 | 0 | 0 | 0 | 1019643
Fuel Taxes | 0 | 0 | 296107 | 0 | 0 | 0 | 0 | 296107
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General Fund | 2525463 | 3425463 | 3425463 | 3602389 | 3694250 | 3788453 | 3730993.0961 | 24192474.0961
Total Revenue | 3545106 | 3425463 | 3721570 | 3602389 | 3694250 | 3788453 | 3730993.0961 | 25508224.0961
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Expense | 3545106 | 3425463 | 3721570 | 3602389 | 3694250 | 3788453 | 3730993 | 25508224
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 3545106 | 3425463 | 3721570 | 3602389 | 3694250 | 3788453 | 3730993 | 25508224

## CHEROKEE & BAYFIELD DRAINAGE
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: CHEROKEE AND BAYFIELD DRAINAGE IMPROVEMENTS
Project Total: $200,000
October 1st, 2019 through September 30th, 2021
Funded Program: #6957111
District(s): 1
Project Description, Milestones and Service Impact
Survey, Engineering, Land Acquisition and Construction of drainage improvements along Cherokee Ave and Bayfield Street. Drainage improvements to include new pipe installation.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Ad Valorem Taxes | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000

## MUCK REMOVAL DISTRICT 2
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: SAVE OUR INDIAN RIVER LAGOON
PROJECT NAME: MUCK REMOVAL-BANANA-MERRITT ISLAND CANALS MUCK DREDGING
Project Total: $1,135,392
Project Timeline: October 01, 2019 through October 01, 2025
Funded Program: 515493
District(s): 2
Project Description, Milestones and Service Impact
The removal of accumulated muck from 30 canals on central Merritt Island with cost share from District 2 maintenance dredging funds, Ad Valorem $400,000. This project will remove approximately 200,000 cubic yards of muck, 80 tons of nitrogen, and 16 tons of phosphorus. Fiscal Year 18-19 Permitting initiated; Fiscal Year 19-20 permits issued; Multi-year construction expected to begin Fiscal Year 21-22.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Ad Valorem | 820809 | 155421 | 159162 | 0 | 0 | 0 | 0 | 1135392
Sales Tax Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unfunded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 820809 | 155421 | 159162 | 0 | 0 | 0 | 0 | 1135392
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Expense | 652904 | 232488 | 250000 | 0 | 0 | 0 | 0 | 1135392
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 652904 | 232488 | 250000 | 0 | 0 | 0 | 0 | 1135392

## BCDC INAMATE SHOWERS
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: FACILITIES
PROJECT NAME: BREVARD COUNTY DETENTION CENTER INMATE SHOWERS REFURBISHMENT
Project Total: $459,308
October 1st, 2018 through September 30th, 2021
Funded Program # 515661
District(s): 1
Project Description, Milestones and Service Impact
This is a multi year project for shower restoration in the main jail. Phase 1 went out to bid for refurbishment of 12 showers and purchasing only received one bidder. With the allocated funds Facilities can restore the remaining 34 showers utilizing Marathon Engineering. A solid epoxy surface removes the possibility for tiles to be removed and use as a weapon. FY20 Funding for the showers had to be reallocated to other projects that exceeded the approved estimated budget. Current construction projects have been coming in higher than estimated.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Charges for Services Revenue | 109308 | 0 | 350000 | 0 | 0 | 0 | 0 | 459308
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unfunded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 109308 | 0 | 350000 | 0 | 0 | 0 | 0 | 459308
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Expense | 109308 | 0 | 350000 | 0 | 0 | 0 | 0 | 459308
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 109308 | 0 | 350000 | 0 | 0 | 0 | 0 | 459308

## BCDC KITCHEN
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: FACILITIES
PROJECT NAME: BREVARD COUNTY DETENTION CENTER REPLACE KITCHEN STEAM BOILER AND PIPING
Project Total: $200,000
October 1st, 2019 through September 30th, 2021
Funded Program # 515976
District(s): 1
Project Description, Milestones and Service Impact
Replace original steam boiler and piping for the kitchen steam kettles. Should the boiler fail, the steam kettles would be down for an extended period of time, cost could be almost double for accelerated bidding/installation. This would also add additional cost to have meals prepared by outsourcing and or alternate methods for inmates and staff. Design has not yet been completed as of April 15th. The Covid19 pandemic has put all projects behind by several months.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Charges for Services Revenue | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unfunded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 23381 | 0 | 0 | 0 | 0 | 0 | 23381
Construction Expense | 0 | 0 | 176619 | 0 | 0 | 0 | 0 | 176619
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 23381 | 176619 | 0 | 0 | 0 | 0 | 200000

## BCGCN HVAC
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: FACILITIES
PROJECT NAME: BREVARD COUNTY GOVERNMENT CENTER NORTH HVAC REPLACEMENT
Project Total: $1,650,000
October 1st, 2020 through September 30th, 2021
Funded Program # 516704
District(s): 1
Project Description, Milestones and Service Impact
Replace 11 existing air-handling units and 2 pre cooling unit that supplies cooling to all 6 floors. Air conditioning units were installed in 1992 when the facility was re-opened after the asbestos abatement project. The current units have reached the end of their useful life. The replacement will be performed under the County-wide HVAC Maintenance Term Contract.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Charges for Services Revenue | 0 | 0 | 1650000 | 0 | 0 | 0 | 0 | 1650000
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unfunded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 0 | 1650000 | 0 | 0 | 0 | 0 | 1650000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 0 | 1650000 | 0 | 0 | 0 | 0 | 1650000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 1650000 | 0 | 0 | 0 | 0 | 1650000

## CSC TSVL HVAC
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: FACILITIES
PROJECT NAME: COUNTY SERVICE COMPLEX TITUSVILLE HVAC IMPROVEMENTS
Project Total: $250,000
October 1st, 2019 through September 30th, 2021
Funded Program # 515974
District(s): 1
Project Description, Milestones and Service Impact
Remove 8 - 30 year old fan coil units from drop ceiling. Install 2 chilled water air handlers, and Trane Tracer controls. Install new ductwork and replace ceiling. This building is used for Sheriffs archives and inmate release registration. Currently there is a dehumidifier is in place for to help eliminate increased humidity and reduce and maintain the environment for any indoor air quality issues. Design completed, there was design issues with the user willing to give up office space for new air handlers.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Charges for Services Revenue | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unfunded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 250000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 20800 | 0 | 0 | 0 | 0 | 0 | 20800
Construction Expense | 0 | 0 | 229200 | 0 | 0 | 0 | 0 | 229200
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 20800 | 229200 | 0 | 0 | 0 | 0 | 250000

## MELB COURTHOUSE ROOF
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: FACILITIES
PROJECT NAME: MELBOURNE COURTHOUSE ROOF FIRST FLOOR ROOF
Project Total: $400,000
May 1st, 2020 through December 30th, 2020
Funded Program # 516576
District(s): 5
Project Description, Milestones and Service Impact
Replace first floor roof portion which has had numerous repairs to the roof over the past several years. The second floor roof was replaced 6 years ago, the lower roof was not replaced as funding was not available and was still manageable. Deferring the roof given the numerous repairs over the years will only continue to deteriorate and cause possible safety issues, environmental issues, structural/interior damage. The roof will be replaced under the countywide roofing term contract.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Charges for Services Revenue | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unfunded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 400000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Construction Expense | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 375000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 400000

## MJC ELEVATORS
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: FACILITIES
PROJECT NAME: PUBLIC ELEVATOR REPLACEMENTS AT HARRY T. & HARRIETTE V. MOORE JUSTICE CENTER
Project Total: $675,000
May 1st, 2020 through March 30th, 2021
Funded Program # 516575
District(s): 4
Project Description, Milestones and Service Impact
Replace the two public elevators as they have reached the end of their useful life. Both public elevators are continuously used during the week and failures have increased to almost a weekly occurrence. The replacement will be performed under the Construction Management at Risk or the Elevator Maintenance Term Contract. Replacement of the remaining elevators will be prioritized and completed over the several budget years.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Charges for Services Revenue | 0 | 675000 | 0 | 0 | 0 | 0 | 0 | 675000
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unfunded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 675000 | 0 | 0 | 0 | 0 | 0 | 675000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 0 | 675000 | 0 | 0 | 0 | 0 | 675000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 675000 | 0 | 0 | 0 | 0 | 675000

## S. ANIMAL SHELTER HUMIDITY
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: FACILITIES
PROJECT NAME: SOUTH ANIMAL SHELTER HUMIDITY ISSUES
Project Total: $175,000
April 1st, 2019 through December 30th, 2020
Funded Program # 6504501
District(s): 5
Project Description, Milestones and Service Impact
Project is to address elevated humidity issue in the offices. Higher humidity issues have the possibility to create mold and mildew issues, along with making the space uncomfortable for the office occupants. Cost has exceeded budget when trying to utilize the Construction Management at Risk contract. Project will be bid out to the mechanical contractors with Brevard County Schools.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Charges for Services Revenue | 175000 | 89130 | 0 | 0 | 0 | 0 | 0 | 264130
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unfunded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 175000 | 89130 | 0 | 0 | 0 | 0 | 0 | 264130
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Expense | 12670 | 870 | 250590 | 0 | 0 | 0 | 0 | 264130
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 12670 | 870 | 250590 | 0 | 0 | 0 | 0 | 264130

## ANGEL AVENUE
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: ANGEL AVENUE DRAINAGE IMPROVEMENTS
Project Total: $110,000
October 1st, 2018 through September 30th, 2021
Funded Program: #6957211
District(s): 2
Project Description, Milestones and Service Impact
Surveying, engineering and construction of a drainage system along the south side of Angel Avenue for the purpose of capturing and conveying road runoff. The service impact for this project will enhance and improve the stormwater system in capture and conveyance capacity.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Ad Valorem Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constitutional Gas Tax | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 110000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 4200
Construction Expense | 0 | 0 | 105800 | 0 | 0 | 0 | 0 | 105800
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 4200 | 0 | 105800 | 0 | 0 | 0 | 0 | 110000

## AURORA SW
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: AURORA ROAD SIDEWALK
Project Total: $1,664,459
June 4 the, 2003 through September 30th, 2022
Funded Program: #6956510
District(s): 5
Project Description, Milestones and Service Impact
Phase I -Design, permitting, acquisition, and construction of improvements of a sidewalk on the north side of Aurora Road from W. of Marywood Lane to Turtlemound. Phase II- Survey and design on the south side from Turtlemound to Wickham Road. Milestones, design completed and right-of-way in the process for Phase I. The service impact for this project will minimize and/or eliminate safety hazard on this corridor and provide pedestrians a more safe walkway.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Ad Valorem Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constitutional Gas Tax | 1664459 | 0 | 0 | 0 | 0 | 0 | 0 | 1664459
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 1664459 | 0 | 0 | 0 | 0 | 0 | 0 | 1664459
Land Expense | 6620 | 0 | 0 | 0 | 0 | 0 | 0 | 6620
Planning/Design Expense | 145104 | 11320 | 0 | 0 | 0 | 0 | 0 | 156424
Construction Expense | 0 | 0 | 1501415 | 0 | 0 | 0 | 0 | 1501415
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 151724 | 11320 | 1501415 | 0 | 0 | 0 | 0 | 1664459

## BABCOCK ST. IMP
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: BABCOCK STREET IMPROVEMENTS
Project Total: $2,500,000
October 18th, 2018 through September 30th, 2021
Funded Program: #6932300
District(s): 3 and 5
Project Description, Milestones and Service Impact
Provide design, permitting, right-of-way acquisition and construction to widen and improve Babcock Street, south of Malabar Road. May include improvements to: intersection, drainage, signals, sidewalk, signage, striping etc. Milestones $2,500,000 matching Grant Agreement with FDOT for the design. This is to facilitate additional capacity and future four lane widening of South Babcock Street. The service level impact will alleviate traffic congestion and provide improved safety and efficiency for the citizens who utilize this roadway.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees |  | 0 |  | 0 | 0 | 0 | 0 | 0
Other Finance Sources | 2500000 | 0 |  | 0 | 0 | 0 | 0 | 2500000
Total Revenue | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 2500000
Construction Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 2500000

## CHICAGO AVE DRP
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: CHICAGO AVENUE DIRT ROAD PAVING
Project Total: $77,000
December 10th, 2019 through November 30th, 2020
Funded Program: #6930507
District(s): 5
Project Description, Milestones and Service Impact
Construct paved road and drainage (east end 300') of Chicago Avenue. This service impact for this project will reduce maintenance and enhance and improve the stormwater system.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 77000
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees |  | 0 |  | 0 | 0 | 0 | 0 | 0
Other Finance Sources |  | 0 |  | 0 | 0 | 0 | 0 | 0
Total Revenue | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 77000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 0 | 77000 | 0 | 0 | 0 | 0 | 77000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 77000 | 0 | 0 | 0 | 0 | 77000

## Corto Road Pipe
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: CORTO ROAD PIPE REPLACEMENT
Project Total: $239,997
May 20th, 2020 through December 31st, 2021
Funded Program: #6964118
District(s): 1
Project Description, Milestones and Service Impact
Installation of approximately 325 LF of 60" Round Concrete Pipe and replace two culvert pipes. The service impact for this project will enhance and improve the stormwater system in capture and conveyance capacity.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 0 | 24997 | 215000 | 0 | 0 | 0 | 0 | 239997
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Finance Sources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 0 | 215000 | 0 | 0 | 0 | 0 | 215000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 24997 | 726.5 | 0 | 0 | 0 | 0 | 25723.5
Construction Expense | 0 | 0 | 214273 | 0 | 0 | 0 | 0 | 214273
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 24997 | 214999.5 | 0 | 0 | 0 | 0 | 239996.5

## FAY & CURTIS SAFETY IMPVMTS
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: FAY AND CURTIS SAFETY IMPROVEMENTS
Project Total: $300,000
December 10th, 2019 through December 31st, 2020
Funded Program: #6936108
District(s): 1
Project Description, Milestones and Service Impact
This project will implement safety improvements in response to the Intersection Safety Study recommendations to include reconstruction of the existing median opening to a bi-directional median opening with off-set left turn lanes. The service impact will provide the citizens a more efficient and safe roadway to travel.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees |  | 0 |  | 0 | 0 | 0 | 0 | 0
Other Finance Sources |  | 0 |  | 0 | 0 | 0 | 0 | 0
Total Revenue | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 20000 |  | 0 | 0 | 0 | 0 | 20000
Construction Expense | 0 | 0 | 280000 | 0 | 0 | 0 | 0 | 280000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 20000 | 280000 | 0 | 0 | 0 | 0 | 300000

## FRIDAY RD & SR 524 INTERSECTION
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: FRIDAY ROAD AND SR524 INTERSECTION IMP
Project Total: $400,000
December 10th, 2019 through December 31st, 2020
Funded Program: #6936109
District(s): 1
Project Description, Milestones and Service Impact
This project includes survey, engineering design, and construction in order to improve the safety and operation of the intersection by adding a dedicated right turn lane on Friday Road southbound approaching SR 524. The service impact will provide the citizens a more efficient and safe roadway to travel.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees |  | 0 |  | 0 | 0 | 0 | 0 | 0
Other Finance Sources |  | 0 |  | 0 | 0 | 0 | 0 | 0
Total Revenue | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 30000 |  | 0 | 0 | 0 | 0 | 30000
Construction Expense | 0 | 0 | 370000 | 0 | 0 | 0 | 0 | 370000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 30000 | 370000 | 0 | 0 | 0 | 0 | 400000

## ELLIS ROAD
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT: ST. JOHNS HERITAGE PARKWAY AND ELLIS ROAD 4-LANE PROJECT
Project Total: $2,731,018
December 1st, 2014 through November 20th, 2021
Funded Program: #6932504
District(s): 5
Project Description, Milestones and Service Impact
This project consists of widening Ellis Road to four lanes from John Rodes Boulevard to just west of Wickham Road 1.7 miles. Signal plans, pavement marking plans, as well as utility coordination and permitting will be a part of this project. The accepted drainage concept will facilitate a final design which should reduce the right-of-way impacts. Drainage analysis completed under design. The service impact for this project will alleviates drainage issues, traffic congestion, and improves the flow of traffic along Ellis Road, SIS connector roadway to the Melbourne Airport and Ellis I-95 interchange.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Bond/Referendum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 2731018 | 0 | 0 | 0 | 0 | 0 | 0 | 2731018
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Finance Sources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 2731018 | 0 | 0 | 0 | 0 | 0 | 0 | 2731018
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 765259.22 | 1165759 | 800000 | 0 | 0 | 0 | 0 | 2731018.22
Construction Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 765259.22 | 1165759 | 800000 | 0 | 0 | 0 | 0 | 2731018.22
0

## HOMESTEAD AVE PIPE
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: HOMESTEAD AVE. PIPE
Project Total: $419,711
August 20th, 2007 through December 31st, 2020
Funded Program: #6957109
District(s): 1
Project Description, Milestones and Service Impact
Replace collapsed cross drains with larger drainage pipes along Homestead Avenue. The service impact for this project will enhance and improve the stormwater system in capture and conveyance capacity.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 419711 | 0 | 0 | 0 | 0 | 0 | 0 | 419711
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Finance Sources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 419711 | 0 | 0 | 0 | 0 | 0 | 0 | 419711
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 49755 |  | 0 | 0 | 0 | 0 | 49755
Construction Expense | 0 | 0 | 369956 | 0 | 0 | 0 | 0 | 369956
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 49755 | 369956 | 0 | 0 | 0 | 0 | 419711

## HOLLYWOOD WIDENING
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: HOLLYWOOD WIDENING PROJECT
Project Total: $9,912,245
August 20th, 2007 through September 30th, 2022
Funded Program: #6932301
District(s): 3
Project Description, Milestones and Service Impact
Design, permitting, right-of-way acquisition, and construction of widening Hollywood Boulevard from US 192 to Palm Bay Road. Milestones, grant for design from Florida Department of Transportation forthcoming. The service impact for this project will relieve traffic congestion in this surrounding community and promote access management.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Bond/Referendum | 3507483.95 | 0 | 0 | 0 | 0 | 0 | 0 | 3507483.95
Constitutional Gas Tax | 1493435 | 0 | 0 | 0 | 0 | 0 | 0 | 1493435
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 4085603 | 0 | 0 | 0 | 0 | 0 | 0 | 4085603
Impact Fees | 825723 | 0 | 0 | 0 | 0 | 0 | 0 | 825723
Total Revenue | 9912244.95 | 0 | 0 | 0 | 0 | 0 | 0 | 9912244.95
Land Expense | 3422467 | 0 | 1889177 | 0 | 0 | 0 | 0 | 5311644
Planning/Design Expense | 879012 | 1000000 | 2000000 | 721589 | 0 | 0 | 0 | 4600601
Construction Expense | 0 | 0 |  |  |  |  | 0 | 0
Other Expense |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 4301479 | 1000000 | 3889177 | 721589 | 0 | 0 | 0 | 9912245

## MICCO BRIDGE
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: MICCO BRIDGE REPLACEMENT
Project Total: $1,500,000
April 7th, 2020 through September 30th, 2022
Funded Program: #6970300
District(s): 3
Project Description, Milestones and Service Impact
This project includes survey, engineering design, and construction as funding becomes available to replace the Micco Bridge, the bridge was constructed in 1938 and has reached the end of its service life. This service impact will provide the citizens a more efficient and safe bridge to travel.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Bond/Referendum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 0 | 500000 | 1000000 | 0 | 0 | 0 | 0 | 1500000
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 500000 | 1000000 | 0 | 0 | 0 | 0 | 1500000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000
Construction Expense | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 1200000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000

## PINEDA OVERPASS
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: PINEDA OVERPASS
Project Total: $26,160,000
August 1st, 2012 through March 30th, 2020
Funded Program: #6963401
District(s): 4
Project Description, Milestones and Service Impact
Construction of an Overpass at Pineda Causeway, to cross the FEC Railroad. A new mast arm traffic signal will be installed at the Holy Trinity school entrance. The service impact for this project alleviates traffic congestion and improves the flow of traffic at Pineda Causeway, as motor vehicle drivers will not have to stop at the railroad tracks, and the on-coming trains will not have to slow down.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Bond/Referendum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 26160000 | 0 | 0 | 0 | 0 | 0 | 0 | 26160000
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 26160000 | 0 | 0 | 0 | 0 | 0 | 0 | 26160000
Land Expense | 3362068.4 | 0 | 0 | 0 | 0 | 0 | 0 | 3362068.4
Planning/Design Expense | 1900831 | 845933 |  | 0 | 0 | 0 | 0 | 2746764
Construction Expense | 1826232 | 8699208 | 9500000 | 0 | 0 | 0 | 0 | 20025440
Other Expense | 25728 |  |  | 0 | 0 | 0 | 0 | 25728
Total Expense | 7114859.4 | 9545141 | 9500000 | 0 | 0 | 0 | 0 | 26160000.4

## RAVEN DRAINAGE & DRP
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: RAVEN DRAINAGE AND DIRT ROAD PAVING
Project Total: $89,000
October 1st, 2018 through September 30th, 2021
Funded Program: #6930205
District(s): 2
Project Description, Milestones and Service Impact
Drainage improvements needed on Raven Road and paving the dirt road will improve the drainage issue. The service impact for this project will enhance and improve the stormwater and require less maintenance on the road due to the paving.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Bond/Referendum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MSTU | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Other Finance Sources | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 64000
Total Revenue | 89000 | 0 | 0 | 0 | 0 | 0 | 0 | 89000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 0 | 89000 | 0 | 0 | 0 | 0 | 89000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 89000 | 0 | 0 | 0 | 0 | 89000

## RIVERSIDE DR SW
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: RIVERSIDE DRIVE SIDEWALK
Project Total: $688,902
November 1st, 2006 through September 30th, 2022
Funded Program: #6956507
District(s): 5
Project Description, Milestones and Service Impact
Design, permitting, and construction of sidewalk along Riverside Drive from Paradise to Eau Gallie Blvd. The service impact of this project provides a safe pedestrian corridor.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Bond/Referendum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 688902 | 0 | 0 | 0 | 0 | 0 | 0 | 688902
Total Revenue | 688902 | 0 | 0 | 0 | 0 | 0 | 0 | 688902
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 75346 | 0 | 0 | 0 | 0 | 0 | 0 | 75346
Construction Expense | 0 | 0 | 613556 | 0 | 0 | 0 | 0 | 613556
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 75346 | 0 | 613556 | 0 | 0 | 0 | 0 | 688902

## SEA RAY BRIDGE REPLACEMENT
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: SEA RAY BRIDGE REPLACEMENT
Project Total: $3,706,384
November 1st, 2006 through September 30th, 2022
Funded Program: #6970200
District(s): 2
Project Description, Milestones and Service Impact
Replacement of Sea Ray Bridge over Sykes Creek (Florida I-Beam): Design Criteria Package and Conceptual Plans are completed, in the process of selecting a Design-Build team. Currently the bridge is closed for safety precautions, when the project is completed the service impact will open the roadway for the motor vehicle drivers and the waterway for boating navigation.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
General Fund | 0 | 805000 | 0 | 0 | 0 | 0 | 0 | 805000
Constitutional Gas Tax | 0 | 1205000 | 1000000 | 0 | 0 | 0 | 0 | 2205000
Fuel Taxes | 0 | 0 | 184840 | 0 | 0 | 0 | 0 | 184840
Incremental Tax from MIRA | 0 | 0 | 255772 | 255772 | 0 | 0 | 0 | 511544
Impact Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 2010000 | 1440612 | 255772 | 0 | 0 | 0 | 3706384
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 410000 | 300000 | 0 | 0 | 0 | 0 | 710000
Construction Expense | 0 | 0 | 2740612 | 255772 | 0 | 0 | 0 | 2996384
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 410000 | 3040612 | 255772 | 0 | 0 | 0 | 3706384
0

## SR520 SYKES CREEK
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: SR520 AND SYKES CREEK INTERSECTION IMPROVEMENTS
Project Total: $600,000
March 29th, 2013 through October 30th, 2020
Funded Program: #6921200
District(s): 2
Project Description, Milestones and Service Impact
This project will upgrade the current intersection functions to include overhead truss signalization, milling, resurfacing and mast arm replacement. Design and permitting complete, construction underway. The service impact will provide the citizens a more efficient and safe roadway to travel.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Finance Sources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 6916.6 | 0 | 0 | 0 | 0 | 0 | 6916.6
Construction Expense | 108083 | 0 | 485000 | 0 | 0 | 0 | 0 | 593083
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 108083 | 6916.6 | 485000 | 0 | 0 | 0 | 0 | 599999.6

## ST. JOHNS PWY
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: ST. JOHNS HERITAGE PARKWAY
Project Total: $52,810,619
July 25th, 2007 through January 30th, 2021
Funded Program: #6930500
District(s): 5
Project Description, Milestones and Service Impact
Construction of the St. Johns Heritage parkway from northern city limits of the City of Palm Bay to west of the Ellis/I-95 Interchange. The southern segment is completed and the northern segment is under construction from US192 north to the new Ellis Interchange, construction anticipated to be completed in October 2019. The service impact for this project will alleviate traffic congestion and improve travel times for commuters, as well as create an evacuation route for those in the northwest quadrant of Palm Bay. Ultimately the Parkway will expand to a southern I-95 interchange near Micco Road, open up southern Palm Bay to new development.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Bond/Referendum | 15841950 | 5268051 | 0 | 0 | 0 | 0 | 0 | 21110001
Fuel Taxes | 0 | 2635227 | 1500000 | 4799301 | 0 | 0 | 0 | 8934528
Grant | 10049811.41 | 3984506.49 | 1425000 | 3963286 | 0 | 0 | 0 | 19422603.9
Impact Fees | 172324 | 853087 | 0 | 0 | 0 | 0 | 0 | 1025411
Other Finance Sources | 499638 | 0 | 1818437 | 0 | 0 | 0 | 0 | 2318075
Total Revenue | 26563723.41 | 12740871.49 | 4743437 | 8762587 | 0 | 0 | 0 | 52810618.9
Land Expense | 7049812.41 | 896342 | 0 | 0 | 0 | 0 | 0 | 7946154.41
Planning/Design Expense | 4251891 | 0 | 0 | 0 | 0 | 0 | 0 | 4251891
Construction Expense | 14064813 | 10991441.89 | 5954809 | 8404303 | 0 | 0 | 0 | 39415366.89
Other Expense | 1197207 | 0 | 0 | 0 | 0 | 0 | 0 | 1197207
Total Expense | 26563723.41 | 11887783.89 | 5954809 | 8404303 | 0 | 0 | 0 | 52810619.3
0

## SHERIDAN RD SW PHASE II
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: SHERIDAN ROAD SIDEWALK PHASE II
Project Total: $640,000
October 1st, 2019 through September 30th, 2020
Funded Program: #6956509
District(s): 5
Project Description, Milestones and Service Impact
Design, permitting, and construction of sidewalk for Phase II of Sheridan Road sidewalk from Sylvan Dr. West to Wickham Road. Phase I was completed in fiscal year 2018 from John Rodes Boulevard to Sylvan Drive West. The service impact of this project provides a safe pedestrian corridor.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 640000
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Finance Sources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 640000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 0 | 640000 | 0 | 0 | 0 | 0 | 640000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 640000 | 0 | 0 | 0 | 0 | 640000

## SUNTREE & WICKHAM
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: SUNTREE BLVD. AND WICKHAM ROAD
Project Total: $400,000
December 10th, 2019 through December 31st, 2020
Funded Program: #6936308
District(s): 4
Project Description, Milestones and Service Impact
This project will upgrade the current intersection by studying the safety and operational needs, evaluating the feasibility of those improvements, and then developing the engineering design for those future intersection improvements. The service impact will provide the citizens a more efficient and safe roadway to travel.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees |  | 0 |  | 0 | 0 | 0 | 0 | 0
Other Finance Sources |  | 0 |  | 0 | 0 | 0 | 0 | 0
Total Revenue | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 30000 |  | 0 | 0 | 0 | 0 | 30000
Construction Expense | 0 | 0 | 370000 | 0 | 0 | 0 | 0 | 370000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 30000 | 370000 | 0 | 0 | 0 | 0 | 400000

## TEAL DRAINAGE & DRP
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: TEAL DRAINAGE AND DIRT ROAD PAVING
Project Total: $89,000
October 1st, 2018 through September 30th, 2021
Funded Program: #6930206
District(s): 2
Project Description, Milestones and Service Impact
Drainage improvements needed on Teal Road and paving the dirt road will improve the drainage issue. The service impact for this project will enhance and improve the stormwater and require less maintenance on the road due to the paving.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Bond/Referendum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MSTU | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Other Finance Sources | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 64000
Total Revenue | 89000 | 0 | 0 | 0 | 0 | 0 | 0 | 89000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
Construction Expense | 0 | 0 | 64000 | 0 | 0 | 0 | 0 | 64000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 89000 | 0 | 0 | 0 | 0 | 89000

## TRAFFIC MC
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROGRAM NAME: TRAFFIC MANAGEMENT/OPERATIONS CENTER
Project Total: $5,603,389
March 21st, 2012 through September 30th, 2023
Funded Program: #6500408
District(s): Countywide
Project Description, Milestones and Service Impact
This project consists of two phases, Phase I is to renovate the storage units for the traffic operations center (TOC) relocation from Merritt Island to the new location on Pineda. Land has been acquired and renovations to the storage units is underway. Phase II is for the architectural and engineering design of the Traffic Management Center (TMC) facility to support not only the current Intelligent Transportation System (ITS) deployment but all future Transportation Systems Management and Operations (ITSM&O) initiatives. The service impact for phase II, the Traffic Management Center will be a control center and will increase the traffic flow efficiency and safety of Brevard County roads.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Bond/Referendum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 5603389 | 0 | 0 | 0 | 0 | 0 | 0 | 5603389
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Finance Sources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 5603389 | 0 | 0 | 0 | 0 | 0 | 0 | 5603389
Land Expense | 178251.74 | 0 | 0 | 0 | 0 | 0 | 0 | 178251.74
Planning/Design Expense | 53355.21 | 200000 | 1510087 | 0 | 0 | 0 | 0 | 1763442.21
Construction Expense | 0 | 312022 | 3346471 | 0 | 0 | 0 | 0 | 3658493
Other Expense | 3008.07 | 193.53 | 0 | 0 | 0 | 0 | 0 | 3201.6
Total Expense | 234615.02 | 512215.53 | 4856558 | 0 | 0 | 0 | 0 | 5603388.55
0

## W. HALL RD OUTFALL IMPRVMTS
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: W. HALL ROAD OUTFALL IMPROVEMENTS
Project Total: $330,000
October 1st, 2018 through November 30th, 2020
Funded Program: #6957212
District(s): 2
Project Description, Milestones and Service Impact
Engineering required to evaluate potential improvements necessary to alleviate reoccurring flooding in the areas adjacent to West Hall Road. The service impact for this project will enhance and improve the stormwater system in capture and conveyance capacity.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Bond/Referendum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MSTU | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Finance Sources | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 330000
Total Revenue | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 330000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
Construction Expense | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 300000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 30000 | 300000 | 0 | 0 | 0 | 0 | 330000

## W. BAY DRIVE DRAINAGE IMPRVMTS
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: WEST BAY DRIVE DRAINAGE IMPROVEMENTS
Project Total: $500,000
October 1, 2020 through September 30, 2021
Funded Program: #6957213
District(s): 2
Project Description, Milestones and Service Impact
Replace existing culvert located between residence 102 and 104 West Bay Drive. The service impact for this project will enhance and improve the stormwater system in capture and conveyance capacity.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Finance Sources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 |  |  | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000

## W. WOOD DRIVE DRAINAGE IMPRVMNT
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: WEST WOOD DRIVE DRAINAGE IMPROVEMENTS
Project Total: $275,000
October 1, 2020 through September 31, 2021
Funded Program: #6957212
District(s): 1
Project Description, Milestones and Service Impact
Replace existing road and drainage infrastructure, between residence #3165 and the east side of Bryan Mawer Drive. The service impact for this project will enhance and improve the stormwater system in capture and conveyance capacity.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 275000
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Finance Sources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 |  |  | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 0 | 275000 | 0 | 0 | 0 | 0 | 275000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 275000 | 0 | 0 | 0 | 0 | 275000

## WICKHAM & AURORA PED IMPVMTS
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: WICKHAM ROAD & AURORA PEDESTRIAN IMPROVEMENTS
Project Total: $100,000
October 1st, 2020 through September 30th,
Funded Program: #6936411
District(s): 4
Project Description, Milestones and Service Impact
This project will construct new pedestrian improvements: additional pedestrian crosswalks and pedestrian signal poles. The service impact will provide the citizens a safer intersection to cross over.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees |  | 0 |  | 0 | 0 | 0 | 0 | 0
Other Finance Sources |  | 0 |  | 0 | 0 | 0 | 0 | 0
Total Revenue | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000

## WICKHAM & LAKE WASHINGTON PED
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME: WICKHAM ROAD AND LAKE WASHINGTON PEDESTRIAN IMPROVEMENTS
Project Total: $100,000
October 1st, 2020 through September 30th,
Funded Program: #6936412
District(s): 4
Project Description, Milestones and Service Impact
This project will construct new pedestrian improvements: additional pedestrian crosswalks and pedestrian signal poles. The service impact will provide the citizens a safer intersection to cross over.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fuel Taxes | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees |  | 0 |  | 0 | 0 | 0 | 0 | 0
Other Finance Sources |  | 0 |  | 0 | 0 | 0 | 0 | 0
Total Revenue | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000

## VALKARIA & WYOMING INTER IMPV
PUBLIC WORKS DEPARTMENT
PROGRAM NAME: TRANSPORTATION CONSTRUCTION
PROJECT NAME :VALKARIA ROAD AND WYOMING ROAD INTERSECTION IMPROVEMENTS
Project Total: $2,817,109
November 1st, 2014 through February, 2021
Funded Program: #6936307
District(s): 3
Project Description, Milestones and Service Impact
Construction of intersection improvements located at Babcock Road and Valkaria Road/Wyoming Road intersection. Design and right-of-way completed, under construction. The service impact for this project will provide a realignment and mast arm signalization of this intersection which will address safety and efficiency for citizens who utilize this roadway.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 | Fiscal Year 2025 & Future | Total Revenue
Constitutional Gas Tax | 860000 | 0 | 0 | 0 | 0 | 0 | 0 | 860000
Fuel Taxes | 1857109 | 0 | 0 | 0 | 0 | 0 | 0 | 1857109
Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impact Fees | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Other Finance Sources | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 2817109 | 0 | 0 | 0 | 0 | 0 | 0 | 2817109
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 258984 | 0 | 0 | 0 | 0 | 0 | 0 | 258984
Construction Expense | 0 | 678439 | 1854900 | 0 | 0 | 0 | 0 | 2533339
Other Expense | 0 | 24786 | 0 | 0 | 0 | 0 | 0 | 24786
Total Expense | 258984 | 703225 | 1854900 | 0 | 0 | 0 | 0 | 2817109