## Bus Shelters
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: BUS SHELTERS
Project Total: $219,416
Project Timeline: October 1st, 2017 through September 30, 2022
Funded Program #: Not Applicable
Project Description, Milestones and Service Impact
In an overall effort to prevent slum and blight, address areas of safety, improve the quality of access to public transportation, enabling employment for those without use of private autos, this project is to facilitate the development, implementation and installation of user-friendly quality bus shelters with identifying markers for the Merritt Island Redevelopment Area along the two main Merritt Island corridors, S.R. 3 and S.R. 520. Average Daily traffic volumes along these corridors combined exceeds 70,000 trips. The infrastructure benefits of bus shelter “stations” will promote multi modal transportation by providing bike racks, less visual blight by controlling litter with composting trash receptacles and cigarette disposal systems. Added solar lighting will deter crime and vandalism and promote safety in slum and blighted areas adjacent to the main corridors. This project will be in partnership with the Space Coast Transportation Planning Organization, Space Coast Area Transit and F D O T.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 4416.18 | 15000 | 120000 | 40000 | 40000 | 0 | 0 | 219416.18 | #REF! | TOTAL VS REV
Grant Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | TOTAL VS EXP
Loans Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 4416.18 | 15000 | 120000 | 40000 | 40000 | 0 | 0 | 219416.18
Land Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 4416.18 | 15000 | 20000 | 10000 | 10000 | 0 | 0 | 59416.18
Construction Expense | 0 |  | 100000 | 30000 | 30000 | 0 | 0 | 160000
Other Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 4416.18 | 15000 | 120000 | 40000 | 40000 | 0 | 0 | 219416.18

## Cone Road
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: CONE ROAD SEPTIC TO SEWER PROGRAM
Project Total: $2,409,484
Project Timeline: October 1st, 2017 through September 30th, 2022
Funded Program #: 6984205
Project Description, Milestones and Service Impact
Currently under construction, this three-phase septic-to-sewer and storm water project to benefit the Indian River Lagoon provides storm water treatment, and sanitary sewer to areas of Merritt Island that are commercial or industrial in use with aging septic systems. This project is a partnership with Brevard County Public Works and Natural Resource Departments as well as a cost-share grant from the St. John’s River Water Management District and pending F D E P grant to facilitate the final phase of construction. Cone Road is a two-lane connector road with no sidewalks, which is bordered by a very deep drainage ditch. Construction is underway and it is anticipated that the construction of the storm water treatment train and bioswale will be completed by the end of 2019 with the sanitary sewer trunk line and laterals available for the private property owners within the industrial park abutting Cone Road. Grant project monitoring will go through the end of 2022.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 |  | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 197097 | 1773887 | 403500 | 15000 | 20000 | 0 | 0 | 2409484 | #REF! | TOTAL VS REV
Grant Revenue | 0 |  |  | 0 | 0 | 0 |  | 0 | #REF! | TOTAL VS EXP
Loans Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 197097 | 1773887 | 403500 | 15000 | 20000 | 0 | 0 | 2409484
Land Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 197097 | 1773887 | 30000 | 15000 | 20000 | 0 | 0 | 2035984
Construction Expense |  |  | 373500 | $ | 0 | 0 | $ | 373500
Other Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 197097 | 1773887 | 403500 | 15000 | 20000 | 0 | 0 | 2409484

## Courtenary
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: SOUTH COURTENAY AND CONE ROAD
Project Total: $325,000
Project Timeline: October 1st, 2018 through September 30th, 2021
Funded Program #: Not Applicable
Project Description, Milestones and Service Impact
This project will facilitate the implementation of solutions for a road safety and capacity issue, a stormwater improvement need along the west side of South Courtenay and a roadway enhancement for the segment that contains a large linear median on the east side approaching Cone Road. This median contains a pedestrian sidewalk and bicycle path that do not meet current safety standards. Enhancement of this area is a supplement but essential project to the work being done on Cone Road. It is anticipated that public input, existing conditions survey, engineering and design of these three components will be underway and completed within 18 months, with construction beginning at the completion of engineering and design.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 0 | 25000 | 50000 | 250000 | 0 | 0 | 0 | 325000 | #REF! | TOTAL VS REV
Grant Revenue | 0 |  | $ | 0 | 0 | 0 | 0 | 0 | #REF! | TOTAL VS EXP
Loans Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 25000 | 50000 | 250000 | 0 | 0 | 0 | 325000
Land Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 |  | $ | 0 | 0 | 0 | 0 | 0
Construction Expense | 0 | 25000 | 50000 | 250000 | 0 | 0 | $ | 325000
Other Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 25000 | 50000 | 250000 | 0 | 0 | 0 | 325000

## Griffis Access
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: GRIFFIS LANDING INFRASTRUCTURE ACCESS
Project Total: $560,000
Project Timeline: October 1st, 2018 through September 30th, 2021
Funded Program #: Not Applicable
Project Description, Milestones and Service Impact
Ongoing facilities improvements at Griffis Landing in conjunction with installation of a new fuel tank and the existing pump out station will increase waterfront usage, adding a sustaining economic benefit for the Landing and its businesses. This project will include a site needs analysis for signage for the fuel dock, lighting for safety, emergency access and A D A compliant access. The dredged depth of the waterway entrance and the consideration of boat traffic lighting and aids to navigation are also enhancements that will be necessary to encourage visitors and enable a safe approach. All feasible construction is anticipated to occur subsequent to the fuel dock installation within the next 12 months. A matching grant for 50% of the dredging cost will be sought from the Florida Inland Navigation Distict (F I N D). Bathymetry and Environmental permitting will be underway in F Y 2019.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 0 | 60000 | 100000 | 200000 | 0 | 0 | 0 | 300000 | #REF! | TOTAL VS REV
Grant Revenue | 0 |  | 0 | 200000 | 0 | 0 | 0 | 200000 | #REF! | TOTAL VS EXP
Loans Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 60000 | 100000 | 400000 | 0 | 0 | 0 | 560000
Land Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 20000
Construction Expense | 0 | 50000 | 90000 | 400000 | 0 | 0 | $ | 540000
Other Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 60000 | 100000 | 400000 | 0 | 0 | 0 | 560000

## Griffis Structural
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: GRIFFIS LANDING STRUCTURAL IMPROVEMENTS
Project Total: $595,594
Project Timeline: October 1st, 2018 through September 30th, 2021
Funded Program #: Not Applicable
Project Description, Milestones and Service Impact
Redevelopment efforts of our remaining working waterfront area offers potential for economic and recreational opportunities, while underscoring the connections between Merritt Island’s community’s culture, built environment, and our natural resources. This project will make it possible to preserve and enhance Griffis Landings' historic structures, home to “Doc’s Bait House” and Ms. Apples Crab Shack, at Brevard County’s only State of Florida designated working waterfront. These two aging structures have suffered multiple hurricanes and exist in a waterfront area subjected to marine related decay. Roof reconstruction and commercial grade impact windows will extend the life of these historic structures. In addition, adaptive reuse of an existing third building on S R 520 for conversion into a working waterfront maritime museum could take place, subject to approval of a pending state grant.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 0 | 100000 | 395594 | 100000 | 0 | 0 | 0 | 300000 | #REF! | TOTAL VS REV
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | TOTAL VS EXP
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 100000 | 395594 | 100000 | 0 | 0 | 0 | 595594
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | $ | 0 | 0 | 0 | 0 | 0 | $
Construction Expense | 0 | 100000 | 395594 | 100000 | 0 | 0 | $ | 300000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 100000 | 395594 | 100000 | 0 | 0 | 0 | 595594

## Merritt Square
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: MERRITT SQUARE MALL AREA COMMERCIAL CORE SUB AREA REDEVELOPMENT
Project Total: $2,100,000
Project Timeline: October 1st, 2018 through September 30th, 2022
Funded Program #: Not Applicable
Project Description, Milestones and Service Impact
The concept for this project originated as part of the 2014 C R A Redevelopment Plan. Given current national retail trends, the aging of the Mall, and the relocation from Merritt Island of several major autombile dealerships, the economic tax base in the Mall Redeveopment area is under seige. The purpose of the project is to engage in an extensive collaborative process, leading towards creation and implementation of catalytic mixed useplace making redevelopment activity in the M I R A Merrit Square Mall Commercial Core Sub Area creating a Merrritt Island Town Centre. The outcome will be creation and phased implemention of a market based highly collaborative concept plan,land and storm water pond acquisition, design,and construction of storm water elements to connect to the Fortenberry Stormwater Treatment Lake at the Veteran’s Memorial Park; feasibility and probable costs of the possible relocation of Fortenberry Road; and an overlay of alternative development standards to facilitate the redevelopment of the Mall and surrounding areas.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 0 | 25000 | 125000 | 1050000 | 900000 | 0 | 0 | 2100000 | #REF! | TOTAL VS REV
Grant Revenue | 0 |  | $ | 0 | 0 | 0 | 0 | $ | #REF! | TOTAL VS EXP
Loans Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 25000 | 125000 | 1050000 | 900000 | 0 | 0 | 2100000
Land Expense | 0 |  | 0 | 1000000 | 0 | 0 | 0 | 1000000
Planning/Design Expense | 0 | 25000 | 125000 | 25000 | 25000 | 0 | 0 | 200000
Construction Expense | 0 |  | $ | 0 | 900000 | 0 | $ | 900000
Other Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 25000 | 125000 | 1025000 | 925000 | 0 | 0 | 2100000

## Plumosa
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: PLUMOSA AND STATE ROAD 520 STORMWATER PIPE EXTENSION
Project Total: $380,000
Project Timeline: October 1st, 2019 through September 30th, 2021
Funded Program #: Not Applicable
Project Description, Milestones and Service Impact
This project is to facilitate the study and engineering of piping stormwater and making the connection of properties at the south east intersection of S R 520 and Plumosa Street to the Stormwater Treatment Lake at the Veteran’s Memorial Park. Approximately seven acres are anticipated for redevelopment and lack this critical connection that will facilitate redevelopment of the blighted car dealership and aging commercial properties along Plumosa Street. Current property is being marketed for development. It is anticipated that the need for this connection will occur within the next 12 months.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 0 |  | 30000 | 350000 | 0 | 0 | 0 | 380000 | #REF! | TOTAL VS REV
Grant Revenue | 0 | $ | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | TOTAL VS EXP
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 |  | 30000 | 350000 | 0 | 0 | 0 | 380000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 |  | 30000 | 20000 | 0 | 0 | 0 | 50000
Construction Expense | 0 | $ | $ | 330000 | 0 | 0 | $ | 330000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 | 0 | 30000 | 350000 | 0 | 0 | 0 | 380000

## Vets
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: VETERAN'S PARK IMPROVEMENTS
Project Total: $1,020,000
Project Timeline: October 1st, 2019 through September 30th, 2020
Funded Program #: Not Applicable
Project Description, Milestones and Service Impact
The purpose of this project is for Merritt Island Redevelopment Agency to partner with Brevard County Parks and Recreation, Department of Natural Resources, and the Veterans Memorial Center, in creation of a Masterplan, and funding the construction phase of the planned Improvements. The Masterplan includes new sidewalks, walking trails, boardwalks, an overall site landscape plan, installation of outlying water and electrical service, and a proposed area for a band shell. In addition, we have an obligation to ensure that the site plan stays active and ensure that permits, plans, and construction stays on track. If funding for the band shell comes to fruition, additional engineering, and site planning will be necessary as well.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 0 |  | 1020000 | 0 | 0 | 0 | 0 | 1020000 | #REF! | TOTAL VS REV
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | TOTAL VS EXP
Loans Revenue | 0 | ` | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 |  | 1020000 | $ | 0 | 0 | 0 | 1020000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | $ | $ | 0 | 0 | 0 | 0 | $
Construction Expense | 0 |  | 1020000 | $ | 0 | 0 | $ | 1020000
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 |  | 1020000 | $ | 0 | 0 | 0 | 1020000

## State Road 3
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: STATE ROAD 3 MULTIMODEL TRANSPORTATION CORRIDOR IMPROVEMENTS
Project Total: $90,000
Project Timeline: October 1st, 2019 through September 30th, 2021
Funded Program #: Not Applicable
Project Description, Milestones and Service Impact
This project is to facilitate the planning and execution of the improvements scheduled by the Space Coast T P O for North Courtenay Parkway, providing M I R A with the opportunity to complete the continuation of Courtenay Parkway street scape and safety upgrades. Sidewalk enhancement and lighting are anticipated elements of the project. Anticipated completion dates rely on approved construction design and engineering. First steps in coordination with Space Coast TPO will involve a review of safety issues, accidents etc. in the form of an access management study. Space Coast T P O will coordinate with M I R A. This would ultimately be a permitted project with the bulk of the funding from FDOT. M I R A or Brevard County would need to be committed to a continuous maintenance program. The F D O T landscape grant could assist in funding a portion of this project.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 0 |  | 40000 | 50000 | 0 | 0 | 0 | 90000 | #REF! | TOTAL VS REV
Grant Revenue | 0 |  | $ | 0 | 0 | 0 | 0 | 0 | #REF! | TOTAL VS EXP
Loans Revenue | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 |  | 40000 | 50000 | 0 | 0 | 0 | 90000
Land Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 |  | 40000 | 50000 | 0 | 0 | 0 | 90000
Construction Expense | 0 |  | $ | $ | 0 | 0 | $ | 0
Other Expense | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 |  | 40000 | 50000 | 0 | 0 | 0 | 90000

## 520
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: NORTH STATE ROAD 520 STORMWATER PROJECT
Project Total: $560,000
Project Timeline: October 1st, 2019 through September 30th, 2022
Funded Program #: Not Applicable
Project Description, Milestones and Service Impact
This project will facilitate engineering, design and implmentation of a small stormwater management project and a water quality issue specifically for the sub-basin north of S.R. 520, east of Plumosa Street to the Sykes Creek area. This area lacks significant stormwater treatment capacity. A large asphalted and blighted area south of the large “health plex”, flooding and safety issues at the intersection of Plumosa Street and East Merritt Avenue are to be addressed.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 0 | 0 | 60000 | 300000 | 200000 | 0 | 0 | 560000 | #REF! | TOTAL VS REV
Grant Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | TOTAL VS EXP
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 | 0 | 60000 | 300000 | 200000 | 0 | 0 | 560000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 | 0 | 30000 | 20000 | 10000 | 0 | 0 | 60000
Construction Expense | 0 | 0 | $ | 0 | 0 | 0 | $ | 0
Other Expense | 0 | 0 | 0 | 300000 | 200000 | 0 | 0 | 500000
Total Expense | 0 | 0 | 30000 | 320000 | 210000 | 0 | 0 | 560000

## 528
MERRITT ISLAND REDEVELOPMENT AGENCY
PROGRAM NAME: MERRITT ISLAND REDEVELOPMENT AGENCY
PROJECT TITLE: STATE ROAD 528 AND STATE ROAD 3 GATEWAY INTERCHANGE
Project Total: $50,000
Project Timeline: October 1st, 2019 through September 30th, 2020
Funded Program #: Not Applicable
Project Description, Milestones and Service Impact
The purpose of this project is to collaborate, facilitate, and create a concept plan for improvements/enhancements with F D O T, Brevard County, and Port Canaveral to take place at the S.R. 3, S.R. 528 and Barge Canal Crossroads. The S.R. 528 Corridor and S.R. 3 Interchange are currently in the F D O T design phase to increase traffic volume/capacity to and from Port Canaveral and the Beaches. The widening of S.R. 528 is planned for six lanes and a bike lane. With the mix of North Merritt Island experiencing growth of new dwelling units, new economic development activity occurring at Cape Kennedy, a proposed Port Canaveral parking garage on S.R. 3, the already frenetic cross roads of S.R. 528 and S.R. 3 with the Barge Canal, Draw Bridge and Sea Ray Drive traffic, the new Cape Crossings development (formerly Tingly Marina), the need for ehnanced curb appeal, and the resulting vehicular stacking and safety problems, are creating a rapidly deteriorating traffic flow situation, adversely affecting mobility and safety for Merritt Island residents, tourists, and workers.
Revenue or Expense Category | All Prior Fiscal Years | Fiscal Year 2019 | Fiscal Year 2020 | Fiscal Year 2021 | Fiscal Year 2022 | Fiscal Year 2023 | Fiscal Year 2024 & Future | Total Revenue | -0- CHECK
Charges for Services Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permit/Fees Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | REV VS EXP
Tax Increment Revenue | 0 |  | 50000 | 0 | 0 | 0 | 0 | 50000 | #REF! | TOTAL VS REV
Grant Revenue | 0 | $ | $ | 0 | 0 | 0 | 0 | $ | #REF! | TOTAL VS EXP
Loans Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | 0 |  | 50000 | $ | 0 | 0 | 0 | 50000
Land Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning/Design Expense | 0 |  | 50000 | 0 | 0 | 0 | 0 | 50000
Construction Expense | 0 | $ | $ | $ | 0 | 0 | $ | $
Other Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expense | 0 |  | 50000 | $ | 0 | 0 | 0 | 50000